## SWOT Worksheet
SWOT Worksheet
Strengths (Cause) | Opportunities (Event)
Corporate Values | Community Involvement
Employee Engagement | Customer Engagement
Positive Public Relations | Employee Integration
Authorized Sales Tent
Weaknesses (Cause) | Threats (Event)
Weather Dependency | Legal and Liability Issues
Limited Participants | Logistical Challenges
Short-Term Impact

## Risk Register Template
Project: Date:
# | Cause | Event | Impact | Risk Owner | Category | Probability Risk Rating | Impact Risk Rating | Risk Score | Trigger | Response
|  | Adverse Weather Conditions | High | Project Manager | Threat | 2 | 3 | 6 |  | Have an indoor backup activity or reschedule the event.
|  | Low Employee Participation | Moderate | HR Manager | Threat | 2 | 2 | 4 |  | Offer rewards or recognition to employees who participate actively.
|  | Logistics and Transportation Issues | High | Logistics Lead | Threat | 1 | 6 | 6 |  | Arrange alternative transportation in case of disruptions.
Total Risk Score
|  | Probability Risk Rating |  | Impact Risk Rating
|  | 5: High |  | 5: High
|  | 4: High to Moderate |  | 4: High to Moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to Low |  | 2: Moderate to Low
|  | 1: Low |  | 1: Low

## Risk Matrix Threats
Project:
P | 5 |  |  |  |  | R1 | Top Risks
R | [6 empty] | # | Cause | Event | Impact | Response
O | 4 |  |  |  |  | R1 | R1 | Adverse Weather Conditions |  | High | Have an indoor backup
B | [6 empty] | R2 | Low Employee Participation |  | Moderate | Offer rewards
A | 3 |  |  |  | R2 |  | R3 | Logistics and Transportation |  | High | Arrange alternative transportation
B | [6 empty] | R4
I | 2 | [5 empty] | R5
L | [6 empty] | R6
I | 1
T | [6 empty] | Scoring
Y |  | 1 | 2 | 3 | 4 | 5 | Watch List Low |  | 1-6
[7 empty] | Watch List Moderate |  | 8-12
| I | M | P | A | C | T | Urgent List High |  | 15-25

## Risk Matrix Opp
Project:
P | 5 |  |  |  |  | R1 | Top Opportunities
R | [6 empty] | # | Cause | Event | Impact | Response
O | 4 | [5 empty] | R1
B | [6 empty] | R2
A | 3 | [5 empty] | R3
B | [6 empty] | R4
I | 2 | [5 empty] | R5
L | [6 empty] | R6
I | 1
T | [6 empty] | Scoring
Y |  | 1 | 2 | 3 | 4 | 5 | Watch List Low |  | 1-6
[7 empty] | Watch List Moderate |  | 8-12
| I | M | P | A | C | T | Urgent List High |  | 15-25