## Communication Plan Template
Communications Plan for Project: Two-Day Seminar and Workshop
Communications Item Forum (What) | Owner (Who-Sender) | Audience (Who-Receiver) | Timing (When) | Format Medium (How) (Where) | Purpose (Why)
Project Updates | Juan Cortez | Team Members, Sandra Morgan | Weekly (Mondays) | Email | Provide progress updates and project status
Agenda Changes | Priya Singh | Team Members, Sandra Morgan | As needed | Email | Notify about changes in the event agenda
Event Logistics | Sarah Kim | Team Members, Hotel Staff | As needed | Email, In-person | Coordinate venue setup, shutdown, and logistics
Technical Support | Sophia Lamar | IT Department, Team Members | As needed | Email, Phone | Address technical issues and IT/AV support
Version: 01 |  |  | Date: Feb 202X