## Blank
Resource Breakdown Structure Project Name: Date:
WBS Identifier # | Work Package | Internal Personal Required | External Personnel Required | Venue Costs | Materials Required | Supplies Required | Equipment Required | Comments | Total Direct Costs
TOTAL COSTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingency Requirements (10%) | [8 empty] | 0
Personnel Cost Requirements | [5 empty] | Note: Update Cost Categories to reflect actual project requirements
Rate | Name | Hours | Costs
0
0
0
0
0
0
0
0
TOTAL |  |  | 0

## Demo Example
Resource Breakdown Structure: "Hierarchical breakout of resources by category and type" Project Name: Annual Executive Meeting Support Project Date: 30 April 20XX
WBS Identifier # | Work Package | Personnel Costs | Beverage Costs | Catering Costs | Support Costs | Venue Support | Comments | Total Direct Costs
1.1.1 | Define Venue |  |  |  |  | 1000 | Initial Deposit | 1000
1.1.2 | Determine Attendees |  |  |  | 1500 |  | Handouts/Print | 1500
1.1.3 | Plan Team | [6 empty] | 0
1.1.4 | Plan Beverages |  | 500 |  |  |  | Coffee/Juice | 500
1.1.5 | Plan Catering |  |  | 1000 |  |  | Box Lunches | 1000
2.1.1 | Assemble Packages | [6 empty] | 0
2.1.2 | Install AV | [6 empty] | 0
2.1.3 | Set Up Venue | [6 empty] | 0
2.1.4 | Conduct Meet |  |  |  | 1000 |  | AV/IT Support | 1000
3.1.1 | Close Out Venue | 600 |  |  |  | 1000 | Clean/Venue $ | 1600
3.1.2 | Prepare Final Reports | [6 empty] | 0
3.1.3 | Pay Outstanding Invoices | 30 |  |  |  |  | Bookkeeper | 30
3.1.4 | Perform Lessons Learned | [6 empty] | 0
TOTAL COSTS |  | 630 | 500 | 1000 | 2500 | 2000 | 0 | 6630
Contingency Requirements (10%) | [7 empty] | 663